# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE VIRGINIA DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (Department) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, the Department has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, the Department aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, the Department has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- “Part A” provided the Department with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensure that each SEA has the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of on-site monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

The Department will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Virginia Department of Education (VDOE) on its progress in implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with the VDOE staff on October 11, 2012, and a follow up exit conference phone call held on October 31, 2012.  Generally, this report does not reflect steps taken by the VDOE after the exit conference.

The report consisits of the following sections:

- Highlights of the VDOE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on October 11, 2012.

- Summary of the VDOE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence the VDOE described during its monitoring phone call on October 11, 2012, through written documentation provided to the Department, and any further clarifications provided by the SEA during its exit conference phone call on October 31, 2012.   Where appropriate, this section also includes a set of “next steps,” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and the VDOE’s approved request.

## Highlights Of The VDOE’s Implementation Of Esea Flexibility

- Based on the information provided during the monitoring conference phone call and through written documentation, the VDOE’s work implementing ESEA flexibility includes the following key accomplishments:

  - Use of an online planning tool to assist priority and focus schools in planning for and implementation of appropriate interventions, including plans to make use of the tool to monitor these schools in real time and thorough training for LEAs on how to make use of the tool.

  - Regular dissemination of information regarding the requirements of Virginia’s ESEA flexibility request using a variety of means, including web site postings, webinars, and email and mail communications, to ensure that all have access to information and are informed about flexibility requirements.

  - Breaking instructions and technical assistance for LEAs on the implementation of the State’s entire flexibility plan into small, manageable steps to help LEAs reduce the stress of implementing all three flexibility principles simultaneously.

## Summary Of the VDOE’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012-2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these local education agencies (LEAs). |
| --- | --- |
| Summary of Progress | The VDOE indicated during the monitoring call that it ran its system of differentiated recognition, accountability, and support, based on 2011–2012 data, in July. The VDOE’s system requires schools be accredited by the state, meet annual measurable objectives (AMOs) that require a 95 percent participation rate and academic progress over time in reading and mathematics, and meet the Federal Graduation Indicator. In issuing accountability determinations, the VDOE discovered that the methodology originally proposed for setting mathematics AMOs did not result in closing achievement gaps between student subgroups. To resolve these issues, the VDOE has proposed a replacement methodology as an amendment to its originally approved request. The VDOE explained that the use of its Gap Group 1 subgroup (which includes students with disabilities, English learners and economically disadvantaged students), in combination with lowering the N-size from 50 to 30, resulted in 99 percent of schools in the State now being issued an accountability determination, based on 2011–2012 data. |
| Next Steps | None. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | The VDOE publicly reported its lists of 36 priority schools, and 72 focus schools on October 10, 2012, by posting the lists on its web site at http://www.doe.virginia.gov/news/news_releases/2012/oct10.shtml (valid as of December 18, 2012). Although public posting did not occur until October 10, all priority and focus schools knew of their designations before posting occurred and have already begun work on planning and implementing interventions. The VDOE has not publicly reported its lists of reward schools. Final determination for all groups of reward schools, particularly the Title I Distinguished schools, will not occur until late December 2012 or early January 2013. |
| Next Steps | To ensure that the VDOE publicly reports its list of reward schools consistent with the principles and timelines of ESEA Flexibility, it must post its list of reward schools no later than January 15, 2013. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying “priority schools” and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | In the 2012–2013 school year, all 36 of the VDOE’s priority schools will implement interventions. Twenty-six of these priority schools are schools receiving School Improvement Grant (SIG) funds to implement one of four SIG models, and 10 of the priority schools are implementing interventions aligned with all of the turnaround principles. All 26 SIG priority schools are already implementing one of the four SIG models. The remaining 10 non-SIG priority schools will be expected to either implement one of the SIG models or a model of their own choosing that meets all of the turnaround principles. The VDOE staff will review any proposed non-SIG models. These schools are currently working on their preliminary improvement plans, which must be uploaded to an online planning tool by January 2013. Detailed plans must be completed by March 2013. The schools must also hire a turnaround partner by January 2013. The VDOE indicates that the instructionally focused portions of the turnaround principles are currently being implemented in these schools. Interventions aligned with other turnaround principles are in the planning stages. The VDOE is tracking the progress of these schools through an online planning tool. Since these schools were in the planning stage as of the monitoring call, the VDOE did not provide evidence that these schools were actively implementing all of the turnaround principles at this time. All priority schools are implementing educator evalaution systems at this time. While the VDOE indicates that it does not have authority to fire teachers or principals, it believes local school boards will use data generated in priority schools to dismiss low performing educators, given that half of the currently implementing SIG schools have already replaced their principals. |
| Next Steps | In order to ensure that implementation of meaningful interventions aligned with all of the turnaround principles takes place in all priority schools for at least three years, the Department will revisit, during Part B monitoring, the status of implementation in non-SIG priority schools and will review evidence and timelines related to this implementation. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as “focus schools” and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | In September the VDOE held a 2-day conference with each LEA contact person and the principals of the focus schools to walk them through the focus school guide and what would be expected of them in the coming year. A second meeting with the LEA contacts on September 24th reemphasized the information. All focus schools are working on developing improvement plans through an online planning tool based on new indicators the state developed for focus schools and based on the needs of the student groups for which the schools were identified. The final session to help schools complete their plans is scheduled for January 10, 2013. As part of their planning process, schools must develop a process for identifying students who will receive interventions. This process will be developed by a school leadership/LEA team that includes Title I, special education, and English language learning specialists. VDOE staff will review and monitor all plans using an online planning tool. |
| Next Steps | None. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012-2013 school year. |
| --- | --- |
| Summary of Progress | The VDOE has identified 482 schools (both Title I and non-Title I) as schools required to create improvement plans based on failure to meet their AMOs. The Title I schools on the list are required to submit their plans in an online planning tool (non-Title I school have the option of using the online planning tool or not). All identified schools’ plans must address three targeted intervention indicators that address the reasons for which they were identified. The VDOE has created tools, including checklists, webinars, and district liaisons to assist these schools in writing and implementing their plans. The VDOE staff will review submitted plans. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools; holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools; and ensuring sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted along with State and local resources.). |
| --- | --- |
| Summary of Progress | While the VDOE is not directly identifying LEAs for intervention, it is requiring LEAs to monitor the plans of schools within the LEAs. The VDOE has selected and contracted with district liaisons for each LEA with identified schools. These contractors will act as liaisons between the SEA and the LEAs. They will monitor school plan development and implementation. The State will review the school plans. The VDOE is also working with staff from the College of William and Mary to conduct site-visits in LEAs and schools. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request; Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility; and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | Using a funding application letter from the State superintendent that went out on October 1, 2012, multiple webinars in the spring and summer of 2012, and a revised application for Federal funds, the VDOE has provided LEAs with information about several potential funding streams they may use to implement interventions. These funding sources include SIG and Title I funds, as well as general improvement funds. LEAs determine what part of the 20 percent set aside they will use to implement the interventions. The VDOE has provided a revised consolidated application for LEAs that addresses use of funds under flexibility. |
| Next Steps | None. |

| Rank Order | The SEA ensures that its LEAs with Title I eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out of rank order. |
| --- | --- |
| Summary of Progress | Not applicable because the VDOE did not request this waiver. |
| Next Steps | None. |