# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE

# RHODE ISLAND DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of onsite monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Rhode Island Department of Education (RIDE) on its progress implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with RIDE staff on September 10, 2012, and a follow-up exit conference held on October 5, 2012.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of RIDE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on September 10, 2012.

- Summary of RIDE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence RIDE described during its monitoring phone call on September 10, 2012, through written documentation provided to ED, and any further clarifications provided by the SEA during its exit conference phone call on October 5, 2012.  When appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and RIDE’s approved request.

## Highlights Of RIDE’s Implementation Of Esea Flexibility

- Based on information provided during the monitoring conference phone call and through written documentation, RIDE’s work implementing ESEA flexibility includes the following key accomplishments:

  - Proactively sharing detailed information about the new accountability system, including dissemination of a “fact sheet” on RIDE’s new accountability system and talking points adapted for each school’s classification that LEAs can use to explain results to parents and the media, resulting in greater understanding and support of the system by stakeholders.

  - Focusing on three factors central to RIDE’s organizational strategy helped to ensure effective implementation: 1) taking advantage of small state size to develop communication and implementation plans for statewide systems, 2) investment in staff capacity and use of a distributed leadership model to include every work team in cross-office activities, and 3) an internal accountability system that includes monitoring of every project and a new data governance structure.

  - Classifying formerly identified Persistently Lowest-Achieving (PLA) schools as priority rather than focus schools and adding 5 newly-identified schools as focus schools, for a total of 29 priority and focus schools combined, a greater number than required under flexibility requirements.

  - Conducting weekly meetings with a subset of LEAs that have a substantial proportion of focus schools in order to address the LEAs’ tactical and strategic needs, planning for schools, and policy issues as part of broader support and oversight for implementation within these LEAs.

### Summary Of RIDE’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | - RIDE indicated that it ran its accountability procedure on June 4, 2012 to determine a Composite Index Score (CIS) that placed schools and LEAs into one of six levels, as described in its approved request. Results from the differentiated system of differentiated recognition, accountability, and support based on 2011–2012 data were posted publicly on July 13, 2012. According to RIDE, no issues arose when the SEA ran its system. |
| Next Steps | None. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | - RIDE publicly reported its lists of 26 reward schools, 18 priority schools, and 11 focus schools by posting the information online on July 13, 2012. (See https://www.eride.ri.gov/eride40/reportcards/12/default.aspx. Link valid as of Jan. 14, 2013). - RIDE confirmed during the exit conference that it classified formerly identified Persistently Lowest-Achieving (PLA) schools as priority rather than focus schools and added five newly identified schools as focus schools, for a total of 29 priority and focus schools combined, a greater number than required under flexibility requirements. |
| Next Steps | None. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | - Materials provided by the SEA confirm that for the 2012–2013 school year, all of RIDE’s 18 priority schools will implement interventions. Twelve of these priority schools are schools receiving School Improvement Grants (SIG) to implement one of four SIG models and six of these priority schools are implementing interventions aligned with all of the turnaround principles. - SIG priority schools in Cohorts 1 and 2 began implementation in 2010–2011 and 2011–2012, respectively. SIG priority schools in cohort 3 began implementing at the start of the 2012-2013 school year. All are now completing the RIDE diagnostic tool to identify instructional needs based on the 2011 performance data. - Non-SIG priority schools are expected to select their specific interventions aligned with all of the turnaround principles within 60 days of completing the diagnostic tool. - In the 2012–2013 school year, LEAs will implement the teacher and principal evaluation model as approved under the State’s Race to the Top grant. Both the principal and teacher evaluation rubrics provide feedback suitable to support decisions about replacement or professional development. Notably, RIDE principals can opt for training to become a turnaround leader and RIDE amended its Race to the Top Scope of Work to increase the number of trainees to accommodate schools identified under ESEA flexibility. - The SEA aims to ensure that LEAs with priority schools are implementing one of the SIG models or interventions aligned with all of the turnaround principles in non-SIG priority schools through a multi-tiered approach. The SEA approves the chosen interventions and approves the plan for implementing the selected models, while considering factors such as alignment between the proposed approach and existing initiatives like Race to the Top. Additionally, the SEA is scheduled to begin quarterly progress monitoring in early winter, which requires LEAs to prepare a quarterly progress monitoring report. The major milestones and outcome measures identified by the LEA are used as the basis for subsequent SEA monitoring. |
| Next Steps | To ensure that the SEA implements meaningful interventions in its SIG-awarded Tier I and/or Tier II schools consistent with the SIG final requirements and, therefore, may continue to count such schools as priority schools, consistent with the principles and timelines in ESEA Flexibility: - The RIDE will work with ED’s Office of School Turnaround to resolve any outstanding monitoring findings relating to the implementation of the SIG models. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | - The SEA documentation indicated that the focus school implementation timeline is the same as the priority school implementation timeline; that is, implementation for all schools is expected to begin in the first semester of the 2012–2013 school year. At the time of the call, the SEA explained that all focus schools were using the State’s diagnostic tool to identify school needs as part of what the State described as a system of “pre-emptive accountability.” Each focus school is expected to complete the diagnostic tool in September, but the SEA has already reviewed the school data and has flagged some issues critical for monitoring subgroup performance. If the school plan submitted does not address these issues, the school must either revise the plan or explain how it will address the needs of subgroup populations. - The SEA indicated the possibility that one focus school would not begin implementation until the second semester. During the exit conference call, RIDE explained that the same planning and oversight process would be followed for this school as for other focus schools. - The SEA is conducting weekly meetings with a subset of LEAs that have a substantial proportion of focus schools in order to address the LEAs’ tactical and strategic needs, planning for schools, and policy issues as part of broader support and oversight for implementation within these LEAs. |
| Next Steps | In order to ensure that implementation of interventions in focus schools is based on the specific academic needs of the school and its students and is consistent with the timelines in ESEA flexibility, ED will revisit, during Part B monitoring, the status of implementation in focus schools and will review evidence and timelines related to this implementation. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | - In addition to priority and focus schools, the RIDE accountability system has also identified “warning schools”. These schools are also required to use the State’s diagnostic tool and select interventions based on the data. The diversity within this group will require different interventions. Determinations will be made on the basis of missing AMOs for subgroups for two years or for subgroups demonstrating very low proficiency. In addition, the CIS will also be used to identify appropriate interventions. The warning schools are located in 10 LEAs that each have an assigned SEA “delegate” to coordinate support services. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: - providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools, - holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools, and - ensuring sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted, along with State and local resources). |
| --- | --- |
| Summary of Progress | - The RIDE Flex Model was designed to address the challenges associated with concentration of the neediest schools in a small number of LEAs. The SEA explained that its goal is to provide supports that would help the LEA scale up interventions across multiple sites. The diagnostic tool is a key factor in this process. - The SEA reports LEA annual performance against their AMOs but does not identify LEAs for corrective actions. As the initial step in planning, each LEA must complete a diagnostic screen that addresses its capacities in the areas of leadership, content and instruction, infrastructure and personnel supports. The SEA oversight system includes quarterly monitoring of LEAs, and RIDE reported that the first monitoring sessions are planned in early winter. - The SEA assigns SEA delegates to LEAs with priority, focus and warning schools. As described in documentation submitted by RIDE, the SEA delegates are members of the Office of Transformation who facilitate and assist the LEAs in moving through the new accountability identification system, from identification to implementation of the selected intervention model, and who function as the first line of contact for the LEAs regarding any questions or concerns related to the new Rhode Island Accountability System under ESEA flexibility. - The SEA provided agendas of meetings conducted by the Office of Transformation during the summer of 2012 that included discussions with LEAs to support the Identification/Early Stage Implementation processes. These meetings included the superintendent of the LEA, selected leadership of the LEA, the SEA delegate, members of the Office and Transformation and SEA leadership representation. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request through Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | - Through memos, FAQs and webinars disseminated in spring 2012, RIDE provided guidance to its LEAs on set-asides and transferability. The SEA explained that it initially monitors allowable uses of funds during its review of LEA Title I applications. Subsequent monitoring includes reviewing LEA implementation of the programs approved by the SEA. |
| Next Steps | None. |

| Rank Order | The SEA ensures that its LEAs with Title I eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of- rank order. |
| --- | --- |
| Summary of Progress | - RIDE has not identified any Title I-eligible high schools with graduation rates below 60 percent as priority schools and, therefore, does not have any LEAs that are taking advantage of the waiver to serve these schools out-of-rank order based on poverty rate. |
| Next Steps | None. |